## Task Estimation
Story ID | Task ID | Task name | Description | Estimate Effort (hrs.) | Committed at Sprint no. | Actual Time | Person
| T001 | fn Login | ฟังก์ชันเข้าสู่ระบบ | 0 | 3 | 0 | X
| T002 | fn SelectInformation | แสดงหน้า Dashboard เมื่อเข้าสู่ระบบ Researcher | 0 | 3 | 0 | X
| T003 | fn SelectResearchGroup | เปลี่ยนจากหน้า Dashboard เป็นหน้า Research group | 0 | 3 | 0 | X
| T004 | fn Database_feild (card 18) |  | 1 | 3 | 1 | James
| T005 | fn Database_Structure (card 18) |  | 1 | 3 | 1 | James
| T006 | fn Edit_admin (card 18) |  | 2 | 3 | 2 | James
| T007 | fn Edit_ResearchGroup (card 18) |  | 4 | 3 | 4 | James
| T008 | แก้ UI (card 18) |  | 4 | 3 | 4 | Mink
| T009 | fn User_Edit (card 18) |  | 2 | 3 | 2 | James
| T010 | fn Visitting_Add (card 18) |  | 3 | 3 | 3 | James
| T011 | fn AddTable (card 18) |  | 1 | 3 | 1 | James
| T012 | fn Security (card 19) |  | 6 | 3 | 6 | James
| T013 | fn Visualize_Data (card 19) |  | 3 | 3 | 3 | James
| T014 | fn Error_log (card 19) |  | 4 | 3 | 4 | James
| T015 | fn Activity_log (card 19) |  | 4 | 3 | 2 | James
| T016 | fn UI_activity (card 19) |  | 2 | 3 | 2 | Mink
| T017 | fn UI_error (card 19) |  | 2 | 3 | 2 | Mink
| T018 | fn UI_visual (card 19) |  | 2 | 3 | 3 | Mink
| T019 | fn QueryAllResearchGroup (card 15) |  | 2 | 3 | 1 | James
| T020 | fn SelectResearchGroup (card 15) |  | 3 | 3 | 1 | James
| T021 | fn QueryAllResearcher (card 15) |  | 2 | 3 | 0.5 | James
| T022 | fn SelectAllResearcher (card 15) |  | 3 | 3 | 0.5 | James
| T023 | fn ResearcherDetail (card 15) |  | 2 | 3 | 1 | Mink
| T024 | fn GrouppingResearcher (card 15) |  | 3 | 3 | 1.5 | Mink
| T025 | แก้ไข Database (card 15) |  | 5 | 3 | 1 | James
| T026 | UAT Test Card18 |  | 4 | 3 | 4 | Mei
| T027 | UAT Test Card19 |  | 4 | 3 | 4 | Mei
| T028 | UAT Test Card15 |  | 4 | 3 | 4 | Mei
| T029 | Test Script |  | 4 | 3 | 4 | Mei
| T030 | Docs | A-DAPT Blueprint, Test report, User manual (.md file), Change log | 8 | 3 | 4 | Mei, Mink
| T031 | แก้ Repository ตาม DoD |  | 2 | 3 | 2 | Mei, Mink
|  |  | เวลารวมทั้งหมด = | 87 |  | 68.5